## Sheet1
		Probability / (In %)	Loss(in % of / total schedule)	Result	Notes

Schedule creation
Schedule, resources, and product definition have all been dictated by the customer or upper management and are not in balance				0
Schedule is optimistic, “best case,” rather than realistic, “expected case”				0
Schedule omits necessary tasks				0
Schedule was based on the use of specific team members, but those team members were not available				0
Cannot build a product of the size specified in the time allocated				0
Product is larger than estimated (in lines of code, function points, or percentage of previous project’s size)				0
Effort is greater than estimated (per line of code, function point, module, etc.)				0
Reestimation in response to schedule slips is overly optimistic or ignores project history				0
Excessive schedule pressure reduces productivity				0
Target date is moved up with no corresponding adjustment to the product scope or available resources				0
A delay in one task causes cascading delays in dependent tasks				0
Unfamiliar areas of the product take more time than expected to design and implement				0
Organization and management
Project lacks an effective top-management sponsor				0
Project languishes too long in fuzzy front end				0
Layoffs and cutbacks reduce team’s capacity				0
Management or marketing insists on technical decisions that lengthen the schedule				0
Inefficient team structure reduces productivity				0
Management review/decision cycle is slower than expected				0
Budget cuts upset project plans				0
Management makes decisions that reduce the development team’s motivation				0
Nontechnical third-party tasks take longer than expected (budget approval, equipment purchase approval, legal reviews, security clearances, etc.)				0
Planning is too poor to support the desired development speed				0
Project plans are abandoned under pressure, resulting in chaotic, inefficient development				0
Management places more emphasis on heroics than accurate status reporting, which undercuts its ability to detect and correct problems				0
Development environment
Facilities are not available on time				0
Facilities are available but inadequate (e.g., no phones, network wiring, furniture, office supplies, etc.)				0
Facilities are crowded, noisy, or disruptive				0
Development tools are not in place by the desired time				0
Development tools do not work as expected; developers need time to create workarounds or to switch to new tools				0
Development tools are not chosen based on their technical merits, and do not provide the planned productivity				0
End-users
End-user insists on new requirements				0
End-user ultimately finds product to be unsatisfactory, requiring redesign and rework				0
End-user does not buy into the project and consequently does not provide needed support				0
End-user input is not solicited, so product ultimately fails to meet user expectations and must be reworked				0
Customer
Customer insists on new requirements				0
Customer review/decision cycles for plans, prototypes, and specifications are slower than expected				0
Customer will not participate in review cycles for plans, prototypes, and specifications or is incapable of doing so—resulting in unstable requirements and time-consuming changes				0
Customer communication time (e.g., time to answer requirements-clarification questions) is slower than expected				0
Customer insists on technical decisions that lengthen the schedule				0
Customer micro-manages the development process, resulting in slower progress than planned				0
Customer-furnished components are a poor match for the product under development, resulting in extra design and integration work				0
Customer-furnished components are poor quality, resulting in extra testing, design, and integration work and in extra customer-relationship management				0
Customer-mandated support tools and environments are incompatible, have poor performance, or have inadequate functionality, resulting in reduced productivity				0
Customer will not accept the software as delivered even though it meets all specifications				0
Customer has expectations for development speed that developers cannot meet				0
Contractors
Contractor does not deliver components when promised				0
Contractor delivers components of unacceptably low quality, and time must be added to improve quality				0
Contractor does not buy into the project and consequently does not provide the level of performance needed				0
Requirements
Requirements have been baselined but continue to change				0
Requirements are poorly defined, and further definition expands the scope of the project				0
Additional requirements are added				0
Vaguely specified areas of the product are more time-consuming than expected				0
Product
Error-prone modules require more testing, design, and implementation work than expected				0
Unacceptably low quality requires more testing, design, and implementation work to correct than expected				0
Development of the wrong software functions requires redesign and implementation				0
Development of the wrong user interface results in redesign and implementation				0
Development of extra software functions that are not required (gold-plating) extends the schedule				0
Meeting product’s size or speed constraints requires more time than expected, including time for redesign and reimplementation				0
Strict requirements for compatibility with existing system require more testing, design, and implementation than expected				0
Requirements for interfacing with other systems, other complex systems, or other systems that are not under the team’s control result in unforeseen design, implementation, and testing				0
Pushing the computer science state-of-the-art in one or more areas lengthens the schedule unpredictably				0
Requirement to operate under multiple operating systems takes longer to satisfy than expected				0
Operation in an unfamiliar or unproved software environment causes unforeseen problems				0
Operation in an unfamiliar or unproved hardware environment causes unforeseen problems				0
Development of a kind of component that is brand new to the organization takes longer than expected				0
Dependency on a technology that is still under development lengthens the schedule				0
External environment
Product depends on government regulations, which change unexpectedly				0
Product depends on draft technical standards, which change unexpectedly				0
Personnel
Hiring takes longer than expected				0
Task prerequisites (e.g., training, completion of other projects, acquisition of work permit) cannot be completed on time				0
Poor relationships between developers and management slow decision making and follow through				0
Team members do not buy into the project and consequently does not provide the level of performance needed				0
Low motivation and morale reduce productivity				0
Lack of needed specialization increases defects and rework				0
Personnel need extra time to learn unfamiliar software tools or environment				0
Personnel need extra time to learn unfamiliar hardware environment				0
Personnel need extra time to learn unfamiliar programming language				0
Contract personnel leave before project is complete				0
Permanent employees leave before project is complete				0
New development personnel are added late in the project, and additional training and communications overhead reduces existing team members’ effectiveness				0
Team members do not work together efficiently				0
Conflicts between team members result in poor communication, poor designs, interface errors, and extra rework				0
Problem team members are not removed from the team, damaging overall team motivation				0
The personnel most qualified to work on the project are not available for the project				0
The personnel most qualified to work on the project are available for the project but are not used for political or other reasons				0
Personnel with critical skills needed for the project cannot be found				0
Key personnel are available only part time				0
Not enough personnel are available for the project				0
People’s assignments do not match their strengths				0
Personnel work slower than expected				0
Sabotage by project management results in inefficient scheduling and ineffective planning				0
Sabotage by technical personnel results in lost work or poor quality and requires rework				0
Design and Implementation
Overly simple design fails to address major issues and leads to redesign and reimplementation				0
Overly complicated design requires unnecessary and unproductive implementation overhead				0
Inappropriate design leads to redesign and reimplementation				0
Use of unfamiliar methodology results in extra training time and in rework to fix first-time misuses of the methodology				0
Product is implemented in a low level language (e.g., assembler), and productivity is lower than expected				0
Necessary functionality cannot be implemented using the selected code or class libraries; developers must switch to new libraries or custom-build the necessary functionality				0
Code or class libraries have poor quality, causing extra testing, defect correction, and rework				0
Schedule savings from productivity enhancing tools are overestimated				0
Components developed separately cannot be integrated easily, requiring redesign and rework				0
Process
Amount of paperwork results in slower progress than expected				0
Inaccurate progress tracking results in not knowing the project is behind schedule until late in the project				0
Upstream quality-assurance activities are shortchanged, resulting in time-consuming rework downstream				0
Inaccurate quality tracking results in not knowing about quality problems that affect the schedule until late in the project				0
Too little formality (lack of adherence to software policies and standards) results in miscommunications, quality problems, and rework				0
Too much formality (bureaucratic adherence to software policies and standards) results in unnecessary, time-consuming overhead				0
Management-level progress reporting takes more developer time than expected				0
Half-hearted risk management fails to detect major project risks				0
Software project risk management takes more time than expected				0
Other
add your own risks				0
add your own risks				0
add your own risks				0
				0
				0
Total				0